Weekly Project Status Report

| Project Name | E-Procurement Project GePNIC |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Report Date | 22nd May 2026 |  |  |  |  |  |
| Project Status Summary |  |  |  |  |  |  |
| Key Tasks Accomplished as on date |  |  |  |  |  |  |
| - WRD & PHED Hands on GePNIC Training Attended: Facilitated coordination and actively participated in the hands-on GePNIC training program conducted by NIC on the Demo Portal on 18th and 20th May 2026 for WRD and PHED officials. - WRD Hands On GePNIC Training Report: The GePNIC hands-on training report for WRD has been completed and shared with the client for review. - PWD GePNIC Training: Successfully coordinated and participated in the GePNIC training program for the PWD Department. - Change Request: Reviewed NIC Response on the Department Change requests and drafted Response Validation Comments and shared with CHiPS - UAT Completion for EMD Collection & Refund Transactions: UAT has been completed for the EMD collection and refund transactions. The files were successfully generated from the NIC end, and the bank has consumed them and shared the response with the NIC team. A few additional sanity checks and test transactions are currently being processed by the NIC and bank teams. - Amendment: The signing of the revised pages of the bank MOU has been completed by CHiPS, and a scanned copy has been shared with the NIC and bank teams. - Integration: A meeting was held with senior bank officials during their visit to the city, where the project status was presented and discussed to help fast-track the integration activities. - Project Milestones & Status Tracker - Milestone-based dashboard tracker has been created and shared with the client for monitoring project progress - Letter to Department for GePNIC trainings: Drafted and shared updated letter to the other departments for GePNIC Training with schedule and agenda. - e-Tendering process flow: -A structured document for the complete e-Tendering process flow as per GePNIC portal has been shared to the client for their review |  |  |  |  |  |  |
| Progress Report |  |  |  |  |  |  |
| S. No. | Action Item | Task Owner | Target Date for Completion | Status (In Progress-Ontime/ In Progress-Delayed/ Completed/ Delayed) | Reasons for delay (if any) | Support reqd from CHiPS/Dept/NIC (if any) |
| 1. | Follow-up on Payment integration between Bank & NIC (As confirmed by the NIC/Bank team, the registration fee collection has been successfully completed. The EMD (Earnest Money Deposit) collection is now scheduled to begin in UAT shortly. | Arijeet Kumar | 29th May 2026 | In Progress-Ontime | - | - |
| 2. | The initial draft of the Data Archival Plan was shared on 11th May 2026, feedback has been received, and the same is being incorporated. | Gayatri Verma | 27th May 2026 | In Progress-Delayed | Discussion has been held on the budgeting for the proposed initiative. | - |
| 3. | Preparation of a structured document for the complete e-Tendering process flow as per GePNIC portal. | Neeraj Pandey | 26th May 2026 | In Progress-Ontime | Preparing a document outlining the complete end-to-end process flow as per GePNIC functionality, similar to the MP State model. | - |
| Upcoming tasks |  |  |  |  |  |  |
| S. No. | Action Item | Task Owner | Target Date for Completion | Status | Dependency | Support reqd from CHiPS/Dept/NIC (if any) |
| 1. | Coordination with NIC and the CSIDC & PWD Departments for Hands-on Training and UAT sign-off of GePNIC e-Procurement System | Gayatri Verma/Vishal Singh/Neeraj Pandey | 29th May 2026 | Yet to Start | CSIDC & PWD has confirmed for hands-on training next week. | NIC/CHiPS |
| 2. | The SOP for the Data Archival Plan shall be prepared initially and circulated among the stakeholders for suggestions and subsequent finalization. | Gayatri Verma | 28th May 2026 | Yet to Start | NA |  |
| 3. | The H2H setup is yet to be completed, as the UAF is still pending signature from CHiPS. The letter for PG MID creation has been submitted by the bank and is awaiting signature by the competent authority. Upon completion of these activities, the documentation phase will be closed. | Arijit Kumar | 29th May 2026 | Yet to Start | NA | - |
| 4. | Production deployment of the Payment Gateway (PG) for Registration Fees and EMD is planned, covering Net Banking and NEFT/RTGS modes along with an online refund mechanism. This will also include the handover of the e-procurement website to CHiPS. | Arijit Kumar | 29th May 2026 | Yet to Start | NA | - |

***